## Relay Build
Desig.	Qty to Fit	Desc	TSA P/N	Qty on PCB	Checkout Verified	Instructions
BIAS-A,BIAS-B	2 x 2W	header pins 100mil single row	CON-PHD-SS-40		OK
BIAS-A,BIAS-B	2	header shunt	CON-JUMPER		OK
C1,3,5,6,8,9	6	Cap Cer SM 100n 1206	CAP-100N-SM		OK
C2	1	10u Tant SMD	CAP-10U-16V-SM1206		OK
C4	1	Elect 1000u 50V Radial	CAP-1000U-E50V		OK	Please do not fit 100uF.
C7	1	Cap Cer SM 1N0 1206	CAP-1N-SM		OK
D1	1	Diode SM 1N4001	DIO-1N4001-SM		OK
D2	1	Diode SM BAT54C	DIO-BAT54C		OK
J1	1	DC Inlet	CON-DC-SKT-PCB		OK
J2		Screw terminal pin headers 24 way	CON-PHD-STERM	1 x 2W	OK	Do not fit.
J3-DB	1	DB9 RA Female	CON-DB9-SKT-RA-PCB		OK
J3-DIN		DIN 8 PCB SKT RA	CON-DIN8-SKTPCB	1	OK	Do not fit.
J3A	1 x 20W	Header skt 0.1” dual row RA	CON-PHD-DR-SKT-40		OK	Fit connector side touching PCB, not up in air.
J3B	1 x 20W	Header pin 0.1” dual row RA	CON-PHD-DR-40		OK	Fit connector side touching PCB, not up in air.
J4		header pins 100mil single row	CON-PHD-SS-40	1 x 6W	OK	Do not fit.
J5		header pins 100mil dual row	CON-PHD-DS-40	1 x 6W	OK	Do not fit.
J9,10	2	Conn RJ45	CON-RJ45PCBSKT8		OK
LED1	1	LED 3MM Red	LED-3MM-RD		OK	Bend leads to mount midway horizontally & vertically between the two RJ45 sockets
LK1		header pins 100mil single row	CON-PHD-SS-40	1	OK	Do not fit.
TP1		header pins 100mil single row	CON-PHD-SS-40	1	OK	Do not fit.
LK1		header shunt	CON-JUMPER	1	OK	Do not fit.
PTC1	1	PTC resettable fuse 1A SMD1206	NON-STOCK
Q1	1	FET SM A3400	FET-A03400A		OK
R1	1	Res SM 300R 1206	RES-300R-SM1206		OK
R5	1	Res SM 3K3 1206	RES-3K3-SM1206		OK
R6	1	Res SM 3K3 1206	RES-3K3-SM1206		OK
R9	1	Res SM 3K3 1206	RES-3K3-SM1206		OK
R13	1	Res SM 3K3 1206	RES-3K3-SM1206		OK
R17	1	Res SM 3K3 1206	RES-3K3-SM1206		OK
R11	1	Res SM 680R 1206	NON-STOCK
R14	1	Res SM 680R 1206	NON-STOCK
R12	1	Res SM 100R 1206	RES-100R-SM1206		OK
R15	1	Res SM 100R 1206	RES-100R-SM1206		OK
R2	1	Res SM 10K 1206	RES-10K-SM1206		OK
R3	1	Res SM 10K 1206	RES-10K-SM1206		OK
R4	1	Res SM 10K 1206	RES-10K-SM1206		OK
R10	1	Res SM 10K 1206	RES-10K-SM1206		OK
R16	1	Res SM 10K 1206	RES-10K-SM1206		OK
R18	1	Res SM 10K 1206	RES-10K-SM1206		OK
R7,19	0	Res SM 0R 1206	RES-0R-SM1206	2	OK	Do not fit.
RLY1-8	8	Relay 5V SPCO	REL-5V-SPDT-QY23		OK
TERM	1 x 2W	header pins 100mil single row	CON-PHD-SS-40		OK
TERM	1	header shunt	CON-JUMPER		OK
U1	1	IC SM MAX485	IC-MAX485CSA		OK
U2	1	Regulator module 5V	REG-MOD5V		OK
U3	1	MAX4820	NON-STOCK		OK
U4	1	IC SM STWD100	NON-STOCK		OK
U5	1	Mod Arduino Pro Mini 8MHz	IC-ARD-PROMINI-3V3		OK	Make sure it's 8MHz/3.3V.
U5	2 x 12W	header pins	CON-PHD-SS-40		OK	Use pins supplied with Arduino
U5	2 x 12W, 2 x 2W	socket strip 100mil single rom	CON-PHD-SKT-SS		OK
U5	2 x 2W	header pins	CON-PHD-SS-40		OK	Mount in A4,A5 & A6,A7 pins.

## Relay Checkout
From `Relay-1' received by email 4/10/22 12:31		From BoM		Board P1
Desig.	Qty	Desc	TSA P/N	PCBA Inspect	Checkout Note
BIAS-A,BIAS-B	2 x 2W	header pins 100mil single row	CON-PHD-SS-40	Not Fitted	Fitted for debug
BIAS-A,BIAS-B	2	header shunt	CON-JUMPER	Not Fitted	Fitted for debug
C1,3,5,6,8,9	6	Cap Cer SM 100n 1206	CAP-100N-SM	OK
C2	1	10u Tant SMD	CAP-10U-16V-SM1206	OK	OK
C4	1	Elect 1000u 50V Radial	CAP-1000U-E50V	100uF/50V fitted	OK
C7	1	Cap Cer SM 1N0 1206	CAP-1N-SM	OK
D1	1	Diode SM 1N4001	DIO-1N4001-SM	OK	OK
D2	1	Diode SM BAT54C	DIO-BAT54C	OK
J1	1	DC Inlet	CON-DC-SKT-PCB	OK	OK
J2	1 x 2W	Screw terminal pin headers 24 way	CON-PHD-STERM	Not Fitted
J3-DB	1	DB9 RA Female	CON-DB9-SKT-RA-PCB	OK
J3-DIN	1	DIN 8 PCB SKT RA	CON-DIN8-SKTPCB	Not Fitted
J3A	1 x 20W	Header skt 0.1” dual row RA	CON-PHD-DR-SKT-40	OK
J3B	1 x 20W	Header pin 0.1” dual row RA	CON-PHD-DR-40	OK
J4	1 x 6W	header pins 100mil single row	CON-PHD-SS-40	Not Fitted	Fitted for debug
J5	1 x 6W	header pins 100mil dual row	CON-PHD-DS-40	Not Fitted	Fitted for debug
J9,10	2	Conn RJ45	CON-RJ45PCBSKT8	OK
LED1	1	LED 3MM Red	LED-3MM-RD	Poking up, should be RA mounted.
LK1	1 x 2W	header pins 100mil single row	CON-PHD-SS-40	Not Fitted	None
TP1	1 x 2W	header pins 100mil single row	CON-PHD-SS-40	Not Fitted	Fitted for debug
LK1	1	header shunt	CON-JUMPER	Not Fitted	None
PTC1	1	PTC resettable fuse 1A SMD1206	NON-STOCK	Not Fitted
Q1	1	FET SM A3400	FET-A03400A	OK
R1	1	Res SM 3K3 1206	RES-3K3-SM1206	OK	Change to 300R
R5	1	Res SM 3K3 1206	RES-3K3-SM1206	OK
R6	1	Res SM 3K3 1206	RES-3K3-SM1206	OK
R9	1	Res SM 3K3 1206	RES-3K3-SM1206	OK	None
R13	1	Res SM 3K3 1206	RES-3K3-SM1206	OK
R17	1	Res SM 3K3 1206	RES-3K3-SM1206	OK
R11	1	Res SM 680R 1206	NON-STOCK	2xR's in parallel	Value confirmed
R14	1	Res SM 680R 1206	NON-STOCK	2xR's in parallel	Value confirmed
R12	1	Res SM 100R 1206	RES-100R-SM1206	OK
R15	1	Res SM 100R 1206	RES-100R-SM1206	OK
R2	1	Res SM 10K 1206	RES-10K-SM1206	OK
R3	1	Res SM 10K 1206	RES-10K-SM1206	OK
R4	1	Res SM 10K 1206	RES-10K-SM1206	OK
R10	1	Res SM 10K 1206	RES-10K-SM1206	4K7 fitted
R16	1	Res SM 10K 1206	RES-10K-SM1206	OK
R18	1	Res SM 10K 1206	RES-10K-SM1206	OK
R7,19	0	Res SM 0R 1206	RES-0R-SM1206	OK
RLY1-8	8	Relay 5V SPCO	REL-5V-SPDT-QY23	OK
TERM	1 x 2W	header pins 100mil single row	CON-PHD-SS-40	Not Fitted	Fitted for debug
TERM	1	header shunt	CON-JUMPER	Not Fitted	Fitted for debug
U1	1	IC SM MAX485	IC-MAX485CSA	OK
U2	1	Regulator module 5V	REG-MOD5V	7805 fitted	Fitted 5V switching reg module.
U3	1	MAX4820	NON-STOCK	OK
U4	1	IC SM STWD100	NON-STOCK	OK
U5	1	Mod Arduino Pro Mini 8MHz	IC-ARD-PROMINI-3V3	16MHZ fitted	Fitted 3.3V 8MHz
U5	2 x 12W	header pins	CON-PHD-SS-40	OK	None
U5	2 x 12W, 2 x 2W	socket strip 2 x 12W	CON-PHD-SKT-SS	2x2w socket not fitted	Fitted 2x2W socket
U5	2 x 2W	header pins	CON-PHD-SS-40	Not Fitted	Fitted

## Relay Test Plan
Category	Action

Preparation	Make test harness to access used pins on RJ45. / ATN will need pullup.	OK
	Check in schematic & PCB files into source control.	OK	Copied from Hardware dir
	Check in BoM doc.	OK	Copied from workbook
	Check in build instructions doc.	OK	Copied from workbook

Pre Power Up	Verify schematic and PCB plots against supplied board to check that you have correct versions.	OK
	Verify BoM. Check correct parts fitted, verify orientation & component values.
	Number all boards and record results tagged with board number.	OK
	Verify board built correctly with no shorts etc.	OK

Power Supply
	Pull all socketed parts and check for shorts between power rails and ground.	OK
	Connect voltmeter to monitor regulated rails.	OK
	Power up via power plug using lab PS set to 12V. Monitor current & regulator output voltages very carefully and be ready to cut power swiftly if required.	OK
	Verify 5V rail voltage & noise.	OK
	Verify 3.3V from Arduino regulator.	OK
	Verify reverse voltage does not damage anything.
	Verify Bus short protection.

Pre Software Checks
	Verify clocks if they start without software configuration. It is surprising how often crystals don't start properly.	OK
	Verify reset signal is inactive.	OK

Upload firmware
	Verify voltages on ISP header before starting.	OK
	Upload firmware with debugger	OK
	Verify crystal if required.	OK
	Check baudrate on console TX line	OK	Wrong baudrate due to 16MHz setting in build and TX/RX reversed in SW.
	Connect serial terminal and check for correct response.	OK

Bus	Verify ground connections.	OK
	Verify 12V connections.	OK
	Verify RS485 A/B bias links.	OK
	Verify RS485 A/B term link.	OK

Analogue	Verify 12V in monitor to ADC.	OK
	Verify 12V bus monitor to ADC.	OK
	Verify Blinky LED.	OK	Very dim, change R1 to 300R.

RS485 Reset	Hold processor in reset	OK
	Verify RS485 not enabled, check voltage on /RE & DE.	OK
	Verify ATN inactive	OK
	Verify RS485 A/B inactive.	OK

RS485	Monitor signals on Bus connector.
	Verify RS485 receive, monitor RO to check waveform.
	Verify ATN drive by setting low with console.	OK
	Verify RS485 transmit, monitor DI to check waveform.	OK

Relays	Verify all relays work and have contacts to correct pins.	OK
	Verify all relays open if WDOG stops toggling.	OK
	Verify DB9 fits	OK
	Verify DIN-8 bits
	Verify power rails on correct pins on 20 pin header.	OK

Finally	Install fresh processor.
	Verify programming by Arduino